## 工作表1
Task ID | Technical description | Restoration duration distribution | Restoration duration minimum (day)* | Restoration duration maximum (day)* | Restoration duration mode (day)* | Resource: Manpower | Resource: Geo-machine | Resource: Crane | Resource: Concrete mixer | Bridge functionality while executing this task
1 | Repair minor spall | Triangular/1 | 3 | 9 | 6 | 2 | 0 | 0 | 1 | 1
2 | Repair minor column crack with epoxy | Triangular/1 | 3 | 9 | 6 | 2 | 0 | 0 | 1 | 1
3 | Submit/review bridge removal plan | Triangular/1 | 10 | 20 | 15 | 0 | 0 | 0 | 0 | 1
4 | submit/review temporary support | Triangular/1 | 20 | 40 | 30 | 0 | 0 | 0 | 0 | 1
5 | Install column (bent) left temporary support | Triangular/1 | 1 | 3 | 2 | 5 | 0 | 1 | 0 | 0
6 | Install column (bent) right temporary support | Triangular/1 | 1 | 3 | 2 | 5 | 0 | 1 | 0 | 0
7 | Remove existing column | Uniform/2 | 3 | 6 | nan | 5 | 0 | 1 | 0 | 1
8 | Place column reinforcement | Uniform/2 | 3 | 6 | nan | 5 | 0 | 1 | 0 | 1
9 | Place column forms | Uniform/2 | 3 | 3 | nan | 5 | 0 | 1 | 0 | 1
10 | Pour column concrete | Uniform/2 | 3 | 6 | nan | 5 | 0 | 1 | 2 | 1
11 | Cure concrete | Triangular/1 | 7 | 12 | 10 | 2 | 0 | 0 | 0 | 1
12 | Remove forms | Uniform/2 | 1 | 1 | nan | 2 | 0 | 1 | 0 | 1
13 | Remove the left temporary support | Uniform/2 | 1 | 1 | nan | 5 | 0 | 1 | 0 | 0
14 | Remove the right temporary support | Uniform/2 | 1 | 1 | nan | 5 | 0 | 1 | 0 | 0
15 | Remove the abutment temporary support | Uniform/2 | 1 | 1 | nan | 5 | 0 | 1 | 0 | 0
16 | Resetting the bearings | Uniform/2 | 1 | 2 | nan | 5 | 0 | 1 | 0 | 0.5
17 | Remove/construct new pedestals | Triangular/1 | 1 | 3 | 2 | 5 | 0 | 0 | 1 | 1
18 | Cure pedestal concrete | Triangular/1 | 7 | 12 | 10 | 1 | 0 | 0 | 0 | 1
19 | Install new bearings | Uniform/2 | 1 | 2 | nan | 5 | 0 | 0 | 0 | 1
20 | Install abutment joint seal assembly | Triangular/1 | 1 | 3 | 2 | 3 | 0 | 0 | 1 | 0.5
21 | Excavate abutment | Uniform/2 | 7 | 12 | 10 | 5 | 2 | 0 | 0 | 0.5
22 | Repair abutment cracks with epoxy | Triangular/1 | 1 | 2 | nan | 2 | 0 | 0 | 1 | 1
23 | Repair abutment spalls | Triangular/1 | 1 | 3 | 2 | 2 | 0 | 0 | 1 | 1
24 | Abutment backfill | Triangular/1 | 1 | 2 | nan | 5 | 2 | 0 | 0 | 0.5
25 | Remove ½ backwall and approach slab | Triangular/1 | 1 | 3 | 2 | 5 | 1 | 1 | 0 | 0.5
26 | Construct ½ backwall | Triangular/1 | 1 | 3 | 2 | 5 | 0 | 1 | 2 | 0.5
27 | Construct ½ approach slab | Uniform/2 | 1 | 2 | 2 | 5 | 1 | 0 | 1 | 0.5
28 | Construct ½ backwall and approach slab | Triangular/1 | 1 | 3 | 2 | 5 | 0 | 1 | 2 | 0.5
29 | Asphalt concrete overlay | Triangular/1 | 1 | 3 | 2 | 3 | 0 | 0 | 1 | 0.5
30 | Mudjacking | Triangular/1 | 1 | 3 | 2 | 3 | 0 | 0 | 1 | 0.5
31 | Install abutment temporary support | Triangular/1 | 1 | 3 | 2 | 5 | 0 | 1 | 0 | 0
32 | Fabricate/procure pipe piles | Triangular/1 | 30 | 40 | 35 | 0 | 0 | 0 | 0 | 1
33 | Excavate bent | Uniform/2 | 3 | 6 | nan | 3 | 1 | 0 | 0 | 0.5
34 | Drive column piles | Triangular/1 | 3 | 9 | 5* | 3 | 1 | 0 | 0 | 1
35 | Place pile forms | Uniform/2 | 3 | 3 | nan | 5 | 0 | 1 | 0 | 1
36 | Place foundation reinforcement | Uniform/2 | 3 | 6 | nan | 5 | 0 | 0 | 0 | 1
37 | Pour foundation concrete | Uniform/2 | 3 | 6 | nan | 5 | 0 | 0 | 2 | 1
38 | backfill | Triangular/1 | 3 | 12 | 5* | 5 | 1 | 0 | 0 | 1
39 | submit /review demo plan for abutment | Triangular/1 | 10 | 20 | 15 | 0 | 0 | 0 | 0 | 1
40 | Excavate abutment/demo wing walls | Uniform/2 | 1 | 3 | nan | 5 | 2 | 0 | 0 | 1
41 | Drive abutment piles | Triangular/1 | 2 | 4 | 3 | 3 | 1 | 0 | 0 | 1
42 | Drill and bond dowels | Uniform/2 | 1 | 2 | 1 | 3 | 0 | 0 | 0 | 1
43 | Construct wing walls | Triangular/1 | 2 | 6 | 4 | 5 | 0 | 0 | 2 | 1
44 | Cure abutment footing | Triangular/1 | 7 | 12 | 10 | 2 | 0 | 0 | 0 | 1
45 | Cure wing walls | Triangular/1 | 7 | 12 | 10 | 2 | 0 | 0 | 0 | 1
46 | Place bent beam reinforcement | Uniform/2 | 1 | 2 | nan | 5 | 0 | 1 | 0 | 1
47 | Place bent beam forms | Uniform/2 | 1 | 2 | nan | 5 | 0 | 1 | 0 | 1
48 | Pour bent beam concrete | Uniform/2 | 2 | 3 | nan | 5 | 0 | 1 | 2 | 1
49 | Remove bent forms | Uniform/2 | 1 | 1 | nan | 2 | 0 | 1 | 0 | 1
50 | Demolish multi-column bent | Uniform/2 | 3 | 6 | nan | 5 | 0 | 1 | 0 | 1
51 | Cure bent beam | Triangular/1 | 7 | 10 | 12 | 2 | 0 | 0 | 0 | 1
52 | Demolition and reconstruction | Triangular/1 | 75 | 300 | 188 | 5# | 2# | 1# | 2# | 0